## Slide 1: Settlement Implementation Impacts of Policy Change
Rocky Boy Montana

## Slide 2: Rocky Boy (Montana)
Chippewa Cree Construction Corp
  Shalee Russette, Project Manager
Advanced Engineering & Environmental Services, Inc
  Deon Stockert, PE

## Slide 3: Location

## Slide 4: Marias River

## Slide 5: History of Marias River
Marias River, river in Glacier county, northwestern Montana, U.S. It is formed by the confluence of Cut Bank, Dupuyer, and Birch creeks and Two Medicine River and flows generally southeastward. The river is impounded by the Tiber Dam to form Lake Elwell, a reservoir used for irrigation and recreation. Beyond the dam it flows for 50 miles (80 km) to enter the Missouri River at Loma. Used by pioneer and trading expeditions, the Marias was named in 1804 by the explorer Meriwether Lewis for his cousin Maria Wood. In 1806 Lewis proceeded up the river to a point near the site of Cut Bank, where Fort Piegan, an American Fur Company trading post, was established in 1831. The river was the site of one of the bloodiest incidents of the Indian Wars when, on January 23, 1870, U.S. soldiers killed 173 Piegan, Blackfoot, and Blood Indians, mostly elderly men, women, and children, in an event that came to be known as the Marias Massacre. The Marias River receives its principal tributary, the Teton River, at Loma, near its junction with the Missouri.
Formed by confluence of the following rivers
  Cut Bank
  Dupuyer
  Birch Creek
  Two Medicine
Impounded by Tiber Dam (Lake Elwell)
Named by Meriwether Lewis for his cousin Maria Wood

## Slide 6
Tiber Dam

## Slide 7: Chippewa Cree Tribe
Reservation Established by Act of Congress in 1916
110,000 Acres in Hill and Chouteau Counties
1 of 7 Reservations in Montana
Bears Paw Mountains
Population = Approx 4,000 (Fastest Growing MT Reservation in 2010 Census)

## Slide 8: Settlement History
1992
2005
1997
1999
2002
2004
The Chippewa Cree Tribe of the Rocky Boy's Reservation passed a resolution approving the water rights compact between the Tribe and the State of Montana.
PL106-163: Federal Water Rights Settlement
On-reservation Water
Off-Reservation (10,000 Acre-Ft)
Water right settlement negotiations began w/ Montana adjudication of water rights.
On-Reservation Projects Bonneau, Towe, East Fork

## Slide 9: Settlement History – Off-Reservation
1992
2005
1997
1999
2002
2004
The Chippewa Cree Tribe of the Rocky Boy's Reservation passed a resolution approving the water rights compact between the Tribe and the State of Montana.
Water right settlement negotiations began w/ Montana adjudication of water rights.
Final Engineering Report
TriPartite OM&R Agreement
PL107-331: Rocky Boy’s/NCMRWS Project
PL106-163: Federal Water Rights Settlement
On-reservation Water
Off-Reservation (10,000 Acre-Ft)

## Slide 10: Settlement History – Off-Reservation
2002
2019
20-Years and not a drop of water On-Reservation.

## Slide 11: Tribal Vision
5.5 MGD to Rocky Boy
  Population
  Removing Water Restrictions
  Improve Water Quantity/Quality
Jobs (PL93-638)
Water Sales (10,000 acre-ft)
Correlate Technical w/ Vision
  Alignment
  Political Buy-In
  Lead Agency Buy-In

## Slide 12: Lead Agency
Chippewa Cree Construction Corporation (CCCC) = Owner/Builder
Bureau of Reclamation = Lead Agency for Construction
Bureau of Indian Affairs = Lead Agency for OM&R
AE2S = Engineer
Project Team

## Slide 13: Federal Funding Structure
Core
Tribal
100% Federal
Authority
80% Federal
10% State Match
10% Local Match
Federal Appropriations
Non-Core
Authority
80% Federal
10% State Match
10% Local Match

## Slide 14: 4 Components
Intake Structure
50% Complete
Core Pipeline
30% Complete
Water Treatment Plant
Bidding Phase
On-Reservation
15% Complete

## Slide 16: Core Pipeline (CCCC)

## Slide 17: Tiber Raw Water Pipelines

## Slide 18: Water Treatment Plant
QR Code

## Slide 19: Water Treatment Plant - Construction

## Slide 20: On-Reservation Water System
Existing Rural Water System = Extremely Supply Limited
Permanent Water Restrictions
Limits Economic Development
Significant Scope changes throughout the changes in DC Administrations

## Slide 21: Administration Changes
Clinton (D) Era – Water Compact 1992-2000 (D/D)
  Baucus (D), Burns(R), Hill (R)
  BOR – Bruce Babbit
Bush (R) – Authorized - 2000-2008 (D/R)
  Baucus (D), Tester (D), Reiberg (R)
  BOR - Gale Norton, Dirk Kempthorne, John Keys
  BIA = Bruce Ward
Obama (D) – Stimulus 2008-2016 (D/D)
  Tester (D), Daines (R), Zinke (R)
  BOR – Ken Salazar, Sally Jewell, Hellekson/Stremcha, Lenny D, Mike Connor
  BIA - Mike Black, Irvin Bekis, Emerson Eskeets
Trump (R) – No ReAuthorization 2016 to Present (R/R)
  Tester (D), Daines (R), Gianforte (R)
  BOR=Ryan Zinke, David Bernhardt, Kruzich, Davies, Black, Mikkelsen
  BIA = Susan Messerly

## Slide 22: FER
Basis for Congress/PL
Lead Agency Follow Explicitly
Underestimated/Overestimated
Basis for Funding Ceiling
Is this Budget Really Sufficient?
Budget Impacts for Future Scope Revisions

## Slide 23: Original Plan (FER)
Intake/WTP
  22 MGD
Core Pipeline
  24-inch (10 MGD max)
On-Reservation Improvements

## Slide 24: 2008 Plan
Revised FER/Scope for More Users
  22 MGD to 36.5 MGD
  Havre, Chester, Brady, Cutbank, etc.
Plans for ReAuthorization
Gravity (to avoid pumping OM&R)
WTP Siting
Hydraulic Modeling Core Pipe
On-Reservation: State/Federal Funds
Intake Superstructure
Core Pipe Procure/Install
CCCC Employee Roster Grows

## Slide 25: 2018 Plan
Don’t Bet on Re-Authorization
Do not Exceed Federal Cap
  Different than Mni Wiconi (OST in SD)
Redesign(s)
  Reevaluate Water Demands for all Users
  Downsize Core Pipe (36 to 30”)
  Downsize WTP Capacity (36.5 mgd to 11 mgd)
  On-Reservation Budget Concerns ($60M to $20M)

## Slide 26: Handling Change
Federal Relationship
  Be Ready
  Design Readiness
Local Relationship
Improvements/Ideas/Modeling
Technical Planning/Flushing
Effective Program Mgt Team

## Slide 27: Program Management
Process of managing Tribe's portfolio of projects to improve program performance:
  Economies of Scale
  Reduced Risk
  Reduced Cost
  Better Communication
  Faster Response Time
  Better Services to Tribal Members
Manages
  Planning
  Funding
  Material
  Labor
  Contractors
  Engineering
  Change Management
  Costs
  Acquisitions
  Environmental, Regulatory
  Resources

## Slide 29: Program Management
Managing Outside Forces and Change Case Studies
  Steel Pipe
  Steel Tariffs
  OM&R
  Master Plan & Tribal Vision
Fight or Adapt
  Is Vision the Same or Revised?

## Slide 30: Case Study – Steel Pipe
Reclamation Design Standards
54 Miles Of Pipe
  DIP ($2.55/gal)
  PVC ($2.94/gal)
  Steel ($3.21/gal)
Technical Memo 8140-CC-2004-1
Steel Decision Added $8M+/-

## Slide 31: Case Study: Project Delivery = Funding
Limited Funding and Project Success, Increasing Ceiling
Increased Funding and Project Success, Paydown of Ceiling

## Slide 32: Effective Implementation Leads to Funding
Lessons
  Authorization Doesn't Mean Appropriation
  Capability to Complete
  Self Perform (638) or Bid
  Labor Pool Skills, Remote Site, etc.
ARRA
  $24M
Negotiations
  Revised Plan in Exchange for Funding Support

## Slide 33: Case Study - OM&R Importance
2002 Trust Fund = $20M
  $15M Tribal & $5M Federal
2010 Trust Fund Needs - $139M
  Federal Contribution via BIA??
2019 - To be Revised
  Alternative Funding = BIA?
Program Mgt Team has been critical to managing this Team

## Slide 34: Weathering the Storm of Change

## Slide 35: Case Study = Master Plan Tribal Vision = Renewed
5.5 MGD to Rocky Boy
  Population
  Removing Water Restrictions
  Improve Water Quantity/Quality
Jobs (PL93-638)
Water Sales (10,000 acre ft)
Corelate Technical w/ that Vision
Alignment
Political Buy-In
Lead Agency Buy-In
LEMONADE
Tero Employment at WTP
Continue Service to NonCore/Havre
Alternative Funding in Future
Peak Supplementation
COMPROMISES
Bid WTP
Downsizing Pipe
Phasing WTP
Capacity Reductions (Non-Core)

## Slide 36: Case Study - Bidding
CCCC Labor Pool
Successful Organization
Production and Professionalism

## Slide 37: Recommendations for Coping With Change
PERFORM
HAVE A CONSISTENT MESSAGE
BE FLEXIBLE
BE PERSISTENT
PLAN
OVERCOME HURDLES

## Slide 38: Questions?
  Deon Stockert, AE2S
  701-690-3693
  Shalee Russette, CCCC
  406-352-8000

## Slide 39
  Deon Stockert, AE2S
  701-690-3693
  Shalee Russette, CCCC
  406-352-8000